## Roadmap
Evidence Room — AP Agent OS
ER Implementation Roadmap — Phases 0–10
Gantt-like dates, owners, status
Agents that earn responsibility.
Phase | Workstream | Owner | Start | End | Status | Exit criteria / pack | Duration (days)
0 | Foundation — readiness & baseline KPIs | Controller / AP Manager | 2026-01-06 | 2026-01-31 | Complete | Free kit + KPI worksheet
1 | Operating model & exception taxonomy | AP Manager | 2026-02-01 | 2026-02-21 | Complete | Starter pack
2 | A01 Intake shadow → draft | AP Ops Lead | 2026-02-22 | 2026-03-21 | In progress | Pilot charter
3 | A04 Triage + A03 Match propose | Exception / Matching Leads | 2026-03-22 | 2026-04-30 | Planned | Controls matrix live
4 | A10 Duplicate signals | Controls Lead | 2026-05-01 | 2026-05-31 | Planned | Precision sampling
5 | A07 Approval propose (narrow) | AP Manager | 2026-06-01 | 2026-06-30 | Planned | SoD tests
6 | A05/A06 GR & PO quality | Receiving / Procurement | 2026-07-01 | 2026-07-31 | Planned | Preventable defects
7 | A08/A09 Resolution & follow-up | Vendor Desk / Ops | 2026-08-01 | 2026-08-31 | Planned | Template approval
8 | Bounded execute for clean match class | Governance Board | 2026-09-01 | 2026-09-30 | Planned | Earn-in review
9 | A11–A14 close & reporting drafts | Close / FP&A | 2026-10-01 | 2026-11-15 | Backlog | Pro library
10 | Scale, Team change pack, Custom edges | AP Manager + Sponsor | 2026-11-16 | 2026-12-31 | Backlog | Team / Custom

## Gantt
Evidence Room — AP Agent OS
Gantt (month markers)
X = active month — illustrative schedule
Agents that earn responsibility.
Phase | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
P0 Foundation — readiness & baseline KPIs | bar: Jan
P1 Operating model & exception taxonomy | bar: Feb
P2 A01 Intake shadow → draft | bar: Feb to Mar
P3 A04 Triage + A03 Match propose | bar: Mar to Apr
P4 A10 Duplicate signals | bar: May
P5 A07 Approval propose (narrow) | bar: Jun
P6 A05/A06 GR & PO quality | bar: Jul
P7 A08/A09 Resolution & follow-up | bar: Aug
P8 Bounded execute for clean match class | bar: Sep
P9 A11–A14 close & reporting drafts | bar: Oct to Nov
P10 Scale, Team change pack, Custom edges | bar: Nov to Dec
Schedule is ILLUSTRATIVE for planning structure — adjust to your capacity.

## Notes
Evidence Room — AP Agent OS
Notes & External Benchmarks
Industry context only — not a guarantee of your results
Agents that earn responsibility.
Field | Value
Source | Ardent Partners — State of ePayables (2025 survey averages)
Avg cost per invoice | $9.84
Exception rate | 18.4%
Straight-through processing (STP) | 35.4%
Label | EXTERNAL BENCHMARK — NOT A GUARANTEE
How to use | Locate your baseline relative to survey averages. Do not substitute these for measured KPIs or treat them as Evidence Room performance claims.
Forbidden use | Do not market 'guaranteed to reach $9.84'. Worksheets labeled ILLUSTRATIVE require your own inputs.
Product | Evidence Room provides methodologies and templates. Humans remain accountable for approvals, payments, and audit representations.

## Disclaimer
Evidence Room — AP Agent OS
Disclaimer
Read before relying on model outputs
Agents that earn responsibility.
Evidence Room products provide educational and operational templates for designing, governing, and measuring AI agents that assist Accounts Payable work.
They are not legal, tax, audit, accounting, investment, or compliance advice.
They are not a substitute for your ERP, AP automation platform, payment provider, or professional advisors.
AI agents can be wrong. Humans remain accountable for approvals, postings, payments, supplier master changes, and representations to auditors.
We do not guarantee any reduction in cost per invoice, cycle time, exception rate, fraud losses, compliance findings, or ROI.
Industry benchmarks attributed to Ardent Partners (2025) — $9.84 avg cost/invoice, 18.4% exception rate, 35.4% STP — are third-party survey averages for context only. Cited only on Notes sheets.
Any cell labeled ILLUSTRATIVE is sample data for structure demonstration — replace with your measured figures before decisions.
Confidential — licensed for internal use by the purchasing organisation.