## Phases
EVIDENCE ROOM · AP AGENT OS
Implementation roadmap
Duration depends on systems, controls, data, and governance. 4–6 weeks is one bounded agent, not the estate.
Phase | Name | Objective | Exit evidence | Typical owner | Status | Start | End
0 | Baseline and readiness | Score diagnostic; name owners; pick slice | Completed scorecard + named registry rows | Transformation + AP Manager | Not started
1 | Process discovery | Observe as-done work | Discovery pack + sample list | Process owner | Not started
2 | Agent specification | Charter for first agent | Signed charter at L0 | Human owner | Not started
3 | Data / tool access | Read paths, allow-list, privacy | Access ticket + DPIA/privacy note | Finance Systems | Not started
4 | Prototype | Offline or boxed run | Prototype log | Owner + FinSys | Not started
5 | Historical testing | Gold-first labelled pack | Scores + confusion notes | Owner + QA | Not started
6 | Shadow mode | Live, no action permissions | Shadow report | Owner | Not started
7 | Controlled execution | Allow-list only, at-most-once | Pilot file + incidents | Owner + Controls | Not started
8 | Performance review | Compare to baseline | Review minutes | AP Manager | Not started
9 | Responsibility progression | One increment if evidence | Promotion pack or stay | Controller + owner | Not started
10 | Scale | Next slice or next agent — not both at once | Updated registry | AP Manager | Not started
ILLUSTRATIVE 4–6 week path for ONE agent (default Intake L0 + Duplicate companion): Phases 0–6 in weeks 1–4, Phase 7 only if evidence, Phase 8–9 in week 5–6. Integrations and DoA delays add time.