## Tracker
EVIDENCE ROOM · AP AGENT OS
Implementation tracker
Team Edition. One increment at a time.
ID | Work item | Phase | Owner | Due | Status | Evidence | Blocker
T-01 | Complete diagnostic scorecard | 0 | [BUYER] |  | Not started
T-02 | Appoint human owners for AG-01 and AG-10 | 0 | AP Manager |  | Not started
T-03 | Select entity × channel × invoice type slice | 0 | AP Manager |  | Not started
T-04 | Observe 8–12 live cases | 1 | Process owner |  | Not started
T-05 | Draft AG-01 charter at L0 | 2 | Intake owner |  | Not started
T-06 | Privacy / access note for invoice images | 3 | Finance Systems |  | Not started
T-07 | Build gold set (labels first) | 5 | QA + owner |  | Not started
T-08 | Shadow week | 6 | Owner |  | Not started
T-09 | Steering paper (no unsigned $) | 8 | Transformation |  | Not started
T-10 | Promotion decision or stay at L0/L1 | 9 | Controller |  | Not started