## Roadmap
EVIDENCE ROOM — Implementation Roadmap Tracker
Phase | Name | Entry criteria | Exit criteria | Owner | Artefacts | Target week | Status | Risks | Notes
0 | Baseline & readiness | Sponsor named | Diagnostic scored; baseline KPIs captured | Transformation | Diagnostic, KPI baseline | 1 | Not started | Low engagement
1 | Process discovery | Access to SMEs | Maps + exception sample coded | AP Manager | Process maps, transcripts | 2-3 | Not started | SME unavailability
2 | Agent specification | Priority use case chosen | Charter + controls approved | AP Manager | Agent charter | 3-4 | Not started | Scope creep
3 | Data / tool access | Security review started | Read access in place | IT/Finance Systems | Access matrix | 4-5 | Not started | Access delays
4 | Prototype | Charter approved | Working prototype on sample | AP Systems | Prototype pack | 5-6 | Not started | Data quality
5 | Historical testing | Prototype ready | Pass thresholds on history | AP Manager | Test report | 6-7 | Not started | Biased sample
6 | Shadow mode | Test gates passed | Shadow KPIs meet gates | AP Manager | Shadow scorecard | 7-9 | Not started | Alert fatigue
7 | Controlled execution | Shadow gates passed | Limited L2/L3 in guardrails | Head of AP | Pilot charter | 9-11 | Not started | Control breach
8 | Performance review | Pilot data in | Go/No-go recorded | Steering | Steering pack | 11-12 | Not started | Vanity metrics
9 | Responsibility progression | Evidence pack complete | Autonomy change logged | Head of AP | Autonomy log | 12+ | Not started | Premature L3+
10 | Scale | One agent stable | Next agents sequenced | Transformation | Scale plan | 12+ | Not started | Parallel overload
Note: Illustrative 4–6 weeks for ONE well-bounded agent. Actual duration depends on systems, controls, integrations, data quality, and governance.