## Working
EVIDENCE ROOM · AP AGENT OS
Implementation roadmap & tracker
Phases 0–10. Dates are examples. Kill criteria live in column Notes.
Phase | Workstream | Task | Owner | Start | End | Status | % | Dependency | Notes
0 | Baseline | Export 90-day volume / exception / cycle | AP Manager | 2026-10-06 | 2026-10-17 | Not started | 0 |  | Unknown is allowed; mark it
0 | Baseline | Cost-per-invoice sketch with Controller | Controller | 2026-10-06 | 2026-10-17 | Not started | 0
1 | Discovery | Observe 8 real invoices | AP SME | 2026-10-13 | 2026-10-24 | Not started | 0 | Phase 0 extract | Include 3 exceptions
2 | Specify | Charter first agent (recommend A05 or A10) | Transformation | 2026-10-20 | 2026-10-31 | Not started | 0 | Discovery | Exclusions first
3 | Access | Read-only invoice/PO/GR/workflow | Finance systems | 2026-10-20 | 2026-11-21 | Not started | 0 |  | Often critical path
5 | Test | Label 50 historical cases + 10 adversarial | AP Quality | 2026-11-03 | 2026-11-21 | Not started | 0 | Access | Gates written first
6 | Shadow | Two-week shadow, no writes | AP Manager | 2026-11-24 | 2026-12-05 | Not started | 0 | Test pass | Disagreement log
7 | Pilot | Level 2 bounded population | Owner | 2026-12-08 | 2027-01-16 | Not started | 0 | Shadow pass | Kill: any critical breach
8 | Review | Promotion decision | Head of AP | 2027-01-19 | 2027-01-23 | Not started | 0 | 4-week window

## Blank
EVIDENCE ROOM · AP AGENT OS
Implementation roadmap & tracker — blank
Reusable. Keep codes stable.
Phase | Workstream | Task | Owner | Start | End | Status | % | Dependency | Notes