## ROADMAP
Illustrative. Actual duration depends on systems, controls, integrations, process complexity, data quality, and governance.
Phase | Name | Intent | Exit criterion | Typical elapsed (one bounded agent) | Status
0 | Baseline and readiness | Sit diagnostic; lock path | Scores + veto notes exist | Week 0 | Not started
1 | Process discovery | Walkthrough + transcript | Map and taxonomy signed | Week 1 | Not started
2 | Agent specification | Charter Wave 1 | Owner, exclusions, packet defined | Week 1–2 | Not started
3 | Data / tool access | Read paths only first | Least-privilege access attested | Week 2 | Not started
4 | Prototype | Historical cases | Scripted cases pass or fail visibly | Week 2–3 | Not started
5 | Historical testing | Sealed hold-out | Accuracy floors recorded | Week 3–4 | Not started
6 | Shadow mode | No action permissions | Shadow report vs human | Week 4–5 | Not started
7 | Controlled execution | L2 packets, limited scope | Kill-switch unused or justified | Week 5–6 | Not started
8 | Performance review | Scorecard | Promote / hold / demote decision | Week 6 | Not started
9 | Responsibility progression | Evidence-gated | Pack complete | After evidence | Not started
10 | Scale | Next category / entity | Same gates, not a skip | After recert | Not started
4–6 weeks is an illustration for one well-bounded agent (e.g. Matching on PO-goods). It is not a commitment.