## Roadmap
Phase | Name | Duration | Activities | Deliverables | Owner | Status
0 | Baseline & Readiness | 1-2 weeks | Run diagnostic, baseline KPIs, secure sponsorship | Readiness score, KPI baseline, charter | AP Manager
1 | Process Discovery | 2-3 weeks | Walkthroughs, transcription, extraction | Process maps, exception taxonomy, RACI | Process Owner
2 | Agent Specification | 1-2 weeks | Define first agent charter, controls, KPIs | Agent spec, control matrix, test plan | AP Manager
3 | Data & Tool Access | 2-4 weeks | API access, data quality, security review | Access granted, data validated | IT / Finance Systems
4 | Prototype | 2-3 weeks | Build agent logic, integrate tools | Working prototype | AI Lead
5 | Historical Testing | 1-2 weeks | Run against historical invoices | Test results, accuracy report | AP Team Lead
6 | Shadow Mode | 2-4 weeks | Agent runs without action permissions | Shadow performance data | AP Manager
7 | Controlled Execution | 4-6 weeks | Limited users/transactions/categories | Pilot results | AP Manager
8 | Performance Review | 1 week | Compare against baseline, QA sample | Performance report | AP Manager
9 | Responsibility Progression | Ongoing | Evaluate autonomy level increase | Autonomy decision record | AP Manager + Controls
10 | Scale | Ongoing | Expand agents, categories, volume | Scaled operating model | Head of Shared Services