## Roadmap
Phase | Name | Objective | Typical duration (indicative) | Entry criteria | Exit criteria | Owner
0 | Baseline & readiness | Diagnostic, KPI baseline, sponsor | 1–2 weeks | Sponsor named | Score + baseline KPIs | Transformation
1 | Process discovery | Observe/transcribe/extract/structure | 1–3 weeks | Slice selected | Maps + taxonomy draft | Process Owner
2 | Agent specification | Charter, exclusions, controls | 1 week | Maps complete | Signed charter L0/L1 | AP Manager
3 | Data/tool access | Least-privilege integrations | 1–4 weeks | Charter signed | Access certified | Systems
4 | Prototype | Limited offline/prototype runs | 1–2 weeks | Access ready | Prototype review notes | AI Architect
5 | Historical testing | Backtest cases | 1–3 weeks | Test set labelled | Accuracy gates met | QA + AP
6 | Shadow mode | Live observe, no action perms | 2–6 weeks | Historical gates met | Shadow KPIs green | AP Manager
7 | Controlled execution | L2 prepare / narrow L3 | 2–8 weeks | Shadow exit | Pilot success criteria | AP Head
8 | Performance review | Evidence pack for autonomy | 1–2 weeks | Pilot complete | Go/No-go | Steering
9 | Responsibility progression | Earn next level | Ongoing | Evidence pack | Updated registry | Transformation
10 | Scale | Next agents / BUs | Ongoing | Stable KPIs | Scaled operating model | CFO sponsor

## Accelerated Example
Illustrative: one well-bounded agent (e.g., Exception Triage L1) in 4–6 weeks
Actual duration depends on systems, controls, integrations, process complexity, data quality, and organisational governance. This is not a commitment.