## Roadmap
Evidence Room · Implementation Roadmap
Phases 0–10. Duration depends on systems, controls, data, and governance — not this grid.
Phase | Name | Primary question | Exit evidence | Owner | Start | End | Status | % complete
0 | Baseline & readiness | What is true today? | Diagnostic score + KPI baseline | AP Manager |  |  | Not started | 0%
1 | Process discovery | How does work actually happen? | Map + taxonomy extract | Process Excellence |  |  | Not started | 0%
2 | Agent specification | What is the job? | Signed charter | Human owner |  |  | Not started | 0%
3 | Data / tool access | What may it read? | Least-privilege grant | Systems Owner |  |  | Not started | 0%
4 | Prototype | Can it produce the pack? | Sample outputs on historic cases | Human owner |  |  | Not started | 0%
5 | Historical testing | Does it hold on a frozen set? | Accuracy / FPR / FNR pack | Quality Lead |  |  | Not started | 0%
6 | Shadow mode | Would we have trusted it? | Shadow vs human log | AP Manager |  |  | Not started | 0%
7 | Controlled execution | Can it act in a box? | Pilot population + incidents | Human owner |  |  | Not started | 0%
8 | Performance review | Did outcomes and controls move? | O + R families | Steering |  |  | Not started | 0%
9 | Responsibility progression | Has it earned the next level? | Registry change + evidence | Head of SSC |  |  | Not started | 0%
10 | Scale | Which population expands? | New charter annex | AP Manager |  |  | Not started | 0%
Illustrative single-agent path (one well-bounded agent): 4–6 weeks. Actual duration depends on ERP access, SoD, data quality, and change control. Not a commitment.