EVIDENCE ROOM

Implementation plan — single agent

Illustrative 4–6 week path. Duration is not a commitment.

Version 1.0 · September 2026 · Licensed material · Flag legal review before customer-facing use as a contract.

Worked example — A05 Goods Receipt, Northline plants 1000–1200

| Week | Work | Exit evidence | Owner |
| --- | --- | --- | --- |
| 0 | Baseline GRNI count and ageing | Extract + O11 baseline | AP Manager |
| 1 | Walkthrough + charter signed at Level 0 | Charter in registry | Receiving Lead |
| 2 | Read-only access + historic packs | 20 historic cases scored | Systems + A05 owner |
| 3–4 | Shadow vs human chase decisions | Agreement log | Receiving Lead |
| 5 | Steering: hold / limited Level 1 drafts via A09 | Decision minute | Head of SSC |
| 6 | Expand plants only if O + R hold | Annex to charter | AP Manager |

Depends on ERP access, SoD, data quality, and organisational governance. Multi-entity and unclear ownership extend the path.

Blank version — complete for your entity

| Field | Your content |
| --- | --- |
| Agent |  |
| Population |  |
| Start level |  |
| Weeks 0–6 work |  |
| Dependencies |  |
| Decline criteria |  |
| Steering date |  |