## Benefits Tracker
Evidence Room · Benefits Realisation
A benefit is not real until Finance signs the cost-base or cash change.
Benefit ID | Hypothesis | Family | Baseline | Observed | Cash? | Signed by | Date signed | Status | Notes
B-01 | Reduce missing-GR open items >5 days | Operational | 420 |  | No |  |  | Open | Capacity / ageing — not cash
B-02 | Reduce repeat E05 price mismatches | Operational | 16% |  | No |  |  | Open | Needs PO quality work
B-03 | Release exception hours | Financial (capacity) | 180 hrs/mo |  | No until conversion |  |  | Open | Apply hours-to-cash
B-04 | Capture incremental early-pay discounts | Financial | $7k/mo opp. |  | Yes if timed |  |  | Open | Do not assume
B-05 | Zero unauthorised payment releases by agents | Risk-control | 0 | 0 | n/a | Payments Lead |  | Control | Must stay true
Unsigned benefits stay at Status=Open. Steering packs must not total unsigned rows into 'savings'.