## Roadmap
Evidence Room — Implementation Roadmap
Illustrative. One well-bounded agent may take 4–6 weeks; actual duration depends on systems, controls, data, governance.
Phase | Name | Objective | Exit criteria | Owner | Start | End | Status | % Complete | Dependencies | Risks
0 | Baseline & readiness | Score maturity and baseline KPIs | Diagnostic complete; baseline recorded |  |  |  | Not started | 0%
1 | Process discovery | Map real AP workflow | Process map + exception list signed |  |  |  | Not started | 0% | Phase 0
2 | Agent specification | Write charter & exclusions | Charter approved |  |  |  | Not started | 0% | Phase 1
3 | Data / tool access | Least-privilege access ready | Access certified |  |  |  | Not started | 0% | Phase 2
4 | Prototype | Build recommend-only prototype | Prototype outputs reviewed |  |  |  | Not started | 0% | Phase 3
5 | Historical testing | Replay historical cases | Accuracy thresholds met or gaps logged |  |  |  | Not started | 0% | Phase 4
6 | Shadow mode | Live observe without action rights | Shadow KPIs stable |  |  |  | Not started | 0% | Phase 5
7 | Controlled execution | Limited prepare/execute guardrails | Pilot exit criteria met |  |  |  | Not started | 0% | Phase 6
8 | Performance review | Formal evidence review | Go/no-go documented |  |  |  | Not started | 0% | Phase 7
9 | Responsibility progression | Earned level change | Dual approval of promotion pack |  |  |  | Not started | 0% | Phase 8
10 | Scale | Expand scope carefully | Scale checklist complete |  |  |  | Not started | 0% | Phase 9