## Agent_registry
EVIDENCE ROOM · AP AGENT OS
Agent registry
One row per living agent. Empty autonomy = do not deploy.
ID | Name | Owner | Level 0-4 | Status | Entities | Exclusions (short) | KPIs | Last review | Kill switch
ER-AP-04 | Exception Triage | AP Ops Mgr | 1 | Shadow | A,B | No close | Accuracy; recode | 2026-09-20 | Head of AP
ER-AP-05 | Goods Receipt | GRNI Lead | 1 | Charter | A | No auto-GR | Receiver error; ageing |  | Head of AP
ER-AP-12 | Payment proposal review | Payments Mgr | 1 | Not started | A | No release | FN on bank change |  | Payments Mgr

## Exception_tracker
EVIDENCE ROOM · AP AGENT OS
Exception tracker
Primary taxonomy code only. Example rows sanitised.
Item | Invoice ref (sanitised) | Value | Age days | Code | Owner role | Agent | Status | Next action | SLA due
E-1044 | INV-7X1 | 18400 | 9 | EX-GR-MISS | Receiver | 05 | Open | Chase | 2026-09-22
E-1045 | INV-2Q9 | 2200 | 3 | EX-PRC | Buyer | 03 | Open | Confirm price | 2026-09-21
E-1046 | INV-9AA | 950 | 1 | EX-DUP-NEAR | Controls | 10 | Review | Compare to INV-9A9 | 2026-09-20

## Control_matrix
EVIDENCE ROOM · AP AGENT OS
Control matrix (working)
Full narrative lives in Controls/00_CONTROL_MATRIX.md
Agent | Risk | Control | P/D | Owner | Evidence | Freq | Escalation
All | Payment authority | No payment role on any agent | P | Payments Mgr | Access review | Q | Any write on payment file
All | Prompt injection | Invoice text untrusted; EX-PIJ | P/D | Security | Quarantine log | C | Any EX-PIJ
05 | Auto-GR | No GR post permission | P | GRNI Lead | Role design | C | Any GR by agent
12 | Missed bank change | Join change log before clear | P | Controls | Review pack | C | Clear with open change
08 | Unreviewed send | Human send default | P | Query Lead | Send log | C | Send without approval

## KPI_scorecard
EVIDENCE ROOM · AP AGENT OS
Weekly scorecard
Separate families. Do not mix vanity with outcomes.
Family | Metric | Baseline | This week | Target (local) | Owner | On track
Activity | Exceptions handled | 0 | 180 |  | Ops
Operational | Classification accuracy (sample) |  | 0.86 | 0.85 | Ops
Operational | Recode rate |  | 0.11 | 0.1 | Ops
Financial | Inference $ | 0 | 42 | 80 | Owner
Financial | Hours released (estimated) | 0 | 6 |  | Owner
Risk | High-risk false negatives in sample | 0 | 0 | 0 | Controls
Risk | Overrides | 0 | 4 |  | Controls

## Roadmap
EVIDENCE ROOM · AP AGENT OS
Implementation roadmap
Actual dates depend on data, controls, integrations.
Phase | Name | Start | End | Owner | Exit criterion | Status
0 | Baseline |  |  | AP Mgr | Diagnostic scored
1 | Discovery |  |  | Process owner | Signed map
2 | Specification |  |  | Agent owner | Charter signed
3 | Access |  |  | IT | Least privilege granted
4 | Prototype |  |  | Tool owner | Sandbox outputs
5 | Historical test |  |  | Owner | Misses explained
6 | Shadow |  |  | Owner | Compare pack
7 | Pilot |  |  | Sponsor | Rollback tested
8 | Review |  |  | Sponsor | Hold/fix/promote
9 | Progression |  |  | Controls + owner | Evidence pack
10 | Scale |  |  | Head of AP | Next agent chosen

## Benefits
EVIDENCE ROOM · AP AGENT OS
Benefits realisation tracker
Only lines with a baseline may be claimed.
Benefit | Baseline | Current | Method | Finance approved Y/N | Notes
Exception hours / month | 660 |  | Volume × rate × minutes | N
Cycle time (days) |  |  | Receipt to ready-to-pay | N
GRNI lines > 14 days |  |  | ERP report | N
Late fees $ | 0 | 0 | AP/Treasury | Y | Do not invent