## Roadmap
Phase | Name | Activities | Duration | Owner | Status | Start Date | End Date | Notes
0 | Baseline & Readiness | Complete diagnostic, establish KPIs, secure sponsorship | 2 weeks | AP Manager | Not Started
1 | Process Discovery | Walkthroughs, transcription, process maps, exception baseline | 3 weeks | Transformation Lead | Not Started
2 | Agent Specification | Select first agent, write charter, define controls | 2 weeks | AP Manager | Not Started
3 | Data & Tool Access | ERP integration, data pipeline, test environment | 3 weeks | IT + AP | Not Started
4 | Prototype | Build agent workflow, configure rules | 2 weeks | Automation Lead | Not Started
5 | Historical Testing | Run against 3-12 months historical data | 2 weeks | AP Analyst | Not Started
6 | Shadow Mode | Agent operates without action permissions | 3 weeks | AP Manager | Not Started
7 | Controlled Execution | Limited users/transactions/categories | 4 weeks | AP Manager | Not Started
8 | Performance Review | Compare against baseline, audit sample | 1 week | Transformation Lead | Not Started
9 | Responsibility Progression | Evaluate autonomy level increase | 1 week | AP Director | Not Started
10 | Scale | Deploy additional agents, expand scope | Ongoing | AP Director | Not Started